## Defect Tracker
Defect ID | Module | Description | Severity | Status | Reported Date | Remarks
DF-01 | Authentication | JWT token not generated due to missing secret key | High | Closed | 2025-02-08 | Environment variable configured
DF-02 | Booking | Seats not released after booking cancellation | Medium | Closed | 2025-02-10 | Seat rollback logic fixed
DF-03 | Pricing Engine | Dynamic price not updating with seat availability | Medium | Closed | 2025-02-12 | Pricing recalculation triggered
DF-04 | Search | Flight search returned empty results for valid routes | Low | Closed | 2025-02-13 | Query filtering corrected
DF-05 | Frontend Navigation | Back button did not return to previous page | Low | Closed | 2025-02-15 | Browser history handling added
DF-06 | Receipt Generation | PDF receipt not generated after successful booking | Medium | Closed | 2025-02-16 | Receipt service integration fixed