## Product Backlog
Backlog ID | Feature | Description | Priority | Milestone | Status
PB-01 | Flight Search | Search flights with dynamic pricing | High | M1 | Done
PB-02 | Dynamic Pricing | Price varies based on seats & demand | High | M2 | Done
PB-03 | Booking API | Create booking and generate PNR | High | M3 | Done
PB-04 | Payment Simulation | Simulate success/failure | Medium | M3 | Done
PB-05 | Cancellation | Cancel booking & release seat | Medium | M3 | Done

## Sprint Backlog
Sprint | Task ID | Task Description | Start Date | End Date | Status
Sprint 1 | T-01 | DB schema & models | 12-11-2025 | 18-11-2025 | Done
Sprint 2 | T-02 | Dynamic pricing logic | 19-11-2025 | 26-11-2025 | Done
Sprint 3 | T-03 | Booking & payment APIs | 27-11-2025 | 24-12-2025 | Done

## Daily Standup
Date | Yesterday Work | Today Plan | Blockers
15-11-2025 | DB setup | Model relations | None
22-11-2025 | Pricing engine | Integrate with API | None
05-12-2025 | Booking logic | Payment API | Minor bugs

## Sprint Review
Sprint | Completed Features | Demo Outcome | Remarks
Sprint 1 | DB + APIs | Successful | All endpoints working
Sprint 2 | Dynamic pricing | Successful | Prices vary correctly
Sprint 3 | Booking & payment | Successful | Deployed on Render

## Sprint Retrospective
Sprint | What Went Well | What Can Improve | Action Items
Sprint 1 | Database schema and core flight search APIs were implemented smoothly | Initial effort estimation and task breakdown accuracy | Refine sprint planning and story point estimation
Sprint 2 | Dynamic pricing logic integration using Python service worked as expected | Test coverage for pricing edge cases and demand simulation | Add automated test cases for pricing scenarios
Sprint 3 | Booking workflow, PNR generation, and concurrency handling were successfully completed | Error handling during booking and payment flow | Improve backend validation and error responses
Sprint 4 | Frontend integration, authentication, and receipt generation were completed successfully | UI performance and user experience consistency | Optimize UI navigation and enhance user feedback messages